## Slide 1: NPR 37805 Payment Posting Automation Using EPIC
Kick Off Meeting May 3rd, 2023

## Slide 2
Agenda
Introduction
Background
Scope
Plan
Risks and Challenges
Communication Plan
Next Steps
Questions

## Slide 3: Project Team
ISS UCLA Team | Operational Leadership
Director: Scott Sherman | Project Sponsor: Kristin Kuntz
Project Team: Noel Serrano – Professional Billing Analyst Christopher “Fig” Figueroa – PB Manager Jeffrey Robinson – PSS Program Analyst Shital Pandya– PSS Manager Sam Dunn – Application Trainer | Stakeholders: Anton Loman – Director of PBO Agustin Flores – Assistant Director of PBO Kathy Carlin – Project Manager

## Slide 4
Project Information
Background
Due to the large volume of electronic remittance advice (ERA) files and multiple dialects of the ERA 835 standard, UCLA-FPG faces significant challenges in processing and posting accurate transactions. This results in high labor costs and delays in recording information, which can impact the allocation of payments to FPG departments.
The Professional Billing Electronic Remittance Pre-Processor (EPP) application was created to address these challenges. EPP has the ability to translate different insurers' ERA 835 dialects into the CareConnect dialect, identify and remove duplicate transactions, and resolve common data inconsistencies. By reducing the number of exceptions that require manual intervention, EPP greatly reduces labor costs and improves the efficiency of transaction processing and posting.
EPP performs a range of checks and updates recommended by PBO, such as updating RMC codes, merging payment amounts, and suppressing certain types of denials.
However, documentation for EPP has not been kept up-to-date, and fixing issues requires extensive resources.
Additionally, the current process lacks the desired development and testing environments, leading to new issues when modifications are made to address bugs.
The version of WebFocus used in EPP is outdated and no longer supported by TIBCO. Upgrading to a newer version may cause issues and require significant resources. Testing may not be possible, leading to instability in the future.

## Slide 5
Project Information
Scope
With the advancements in Epic, we propose to start transitioning EPP processes into Epic where appropriate and reduce our reliance on EPP for remittance processing.
To achieve this goal, we will review each payer's remittance processing requirements and provide recommendations on what can be moved into Epic.
Our approach will include:
  Review the existing EPP logic to determine its continued relevance and feasibility, including assessing the potential for replication within Epic.
  Conducting extensive testing of unaltered remittance files in the PSUP environment to identify automation opportunities, compare data with EPP remittance files, and present workflow decisions to operational leaders for next steps.
  Developing automation within Epic for remittance files.
  Developing documentation for edits within EPP and Epic.
  Developing training documentation and integrating it into the current training strategy.
  Evaluating the frequency of each workflow to determine if it should be included in the larger training strategy.
  Develop and/or maintain current EPP reports.

## Slide 6: High Level Deliverables
Team | Deliverables
Professional Billing | Analysis report detailing the current state of ERA 835 processing and identifying pain points and areas for improvement. Recommendations report outlining potential solutions to address identified pain points, including EPP and Epic replication options. Testing plan detailing the various test scenarios that will be used to validate the effectiveness of the new ERA 835 processing procedures and systems. Final report summarizing the results of the project and detailing the improvements achieved in ERA 835 processing Create and/or maintain reports that are currently sent to operations.
Physician Support Services | Review scripts with PB Analyst and document EPP process Retire existing EPP process
Operation/Stakeholders | Updated procedures and policies outlining new processes for ERA 835 processing Review EPP process and determine its continued relevance. Make decisions on items that can’t be replicated in Epic
Training | Training materials: Develop and deliver training materials for the new processes and tools that will be implemented as part of the project.

## Slide 7
Project Information
Plan
To ensure that the processing of remittance files remains smooth and to simplify issue resolution, we will adopt a phased approach for the project. This approach involves revising a limited number of RMOs during each phase, which will allow for better control over the implementation process and reduce the risk of disruption to critical operations. This will allow us to send payer files directly to Epic without EPP pre-processing the file.
Each phase will include the following:
  Identify payer files processed by the RMO.
  3 to 4 weeks of data analysis by reviewing scripts and loading files into a support environment to identify EPP revisions for each payer. In tandem reviewing and documenting the EPP code.
  1 week for operations to review and approve decisions related to project
  1-2 week of build and testing/validation per phase.
  1-2 week of workflow walkthrough and approval gathering
  1 week of post-implementation validation and issue resolution.
Once the RMO(s) has been updated, we will review the next phase with operations to identify next steps.

## Slide 8
2023
2023
May
Jun
Jul
20 days
May 3- May 30
Data analysis and documentation
5 days
10 days
Jun 8 - Jun 20
Build and testing
5 days
May 31 - Jun 7
Review and approval for Operations
10 days
Jul 5 – Jul 11
Go-Live & Stabilization
5 days
Jun 21 – Jul 4
Workflow walkthrough and approval
Go / No-Go
Jun 28
Kickoff
May 3
Go-Live
Jul 5
Next Phase
Jul 12
High Level Timeline
Today
Training
Jun 26 – Jun 30
Spring 2023 Upgrade
May 20
2024
May
Jun
Feb
May 3- Jul 11
Phase I (MCR, Medi-Cal)
Oct 4 – Dec 5
Phase III (Workers Comp and Misc)
Jul 12 – Oct 3
Phase II (BC, Aetna, UHC, Cigna, etc)
Phase IV (Tapestry)
Dec 6 – Mar 5
2023
Jul
Aug
Sep
Oct
Nov
Dec
Jan
Mar

## Slide 9: Communication Plan
Communication | Description | Frequency | Date/Time | Facilitator | Method
IT Project Status Report | Overall health of the project. To include a timeline, risks, upcoming milestones. | Bi-Weekly | 2nd and 4th Friday of the Month | Noel Serrano | Uplan
Governance Meeting | Review project status, risks, and discuss decisions to be made. | Bi-Weekly | Wednesdays at 8am | Noel Serrano | Zoom
Governance Meeting Minutes | Meeting minutes from Stakeholder meeting. Includes updates, project status, risks, action items. | Bi-Weekly | 24 hours after Stakeholder Meeting | Noel Serrano | Email
Research and analysis meeting | Review and analyze scripts and document findings. | 1-2 Week | TBD | Noel Serrano | Zoom
Training meeting | Review current process and upcoming changes to workflow | 2-3 weeks before go-live | TBD | Noel Serrano | Zoom
Notes: Any operational meetings?

## Slide 10
Project Information
Risks and Challenges
Data Integrity: Risk of data errors due to manual data entry.
Resource Availability: Availability of resources to support both Epic and EPP systems.
User Acceptance: User acceptance of the new system and changes to workflow processes.
Implementation Delays: Delays in implementation due to unforeseen technical issues or resource constraints.
Testing and Validation: Risk of insufficient testing and validation leading to errors and downtime.
Training and Documentation: Adequate training and documentation to ensure successful adoption of the new system.

## Slide 11
Project Information
Out of Scope
  Self Pay / Bad Debt files
  Tapestry Medicare Advantage project
  Additional new features or functionalities that were not part of the original scope or requirement.
Assumptions
Decisions will be made within the allotted time and responsive throughout the project.
Go-live will be planned after month-end to eliminate issues that could arise.
Constraints
Go-live support for Epic 2023 upgrade
Resource constraints due to upcoming holiday outages.
Tapestry Medicare Advantage project

## Slide 12
Project Documentation
Box
  https://uclahs.app.box.com/folder/197103730115
  Action Items/Risks/Issues
    PM
      Create Action Items/Risks/ Issues in UPlan taken during status meetings
      Will be reviewed during status meetings
  Project Team
    Track progress on each action item/risk/issue with work notes in Uplan and Box
    Create wiki articles for all workflows and action items
  Change Tickets
    Will be labeled with NPR 37805 in CHAPP/CHG

## Slide 13
Next Steps
Establish a reoccurring meeting with Jeff to review.
Document current EPP process and review if Epic can perform same functionality.
If Epic cannot perform same functionality, bring options to stakeholders for decision.

## Slide 14
Questions